## Sheet1
Project Warmup
Project Phase | Milestones | dates
P1: Recommend system | find dataset | 2022-09-25
| EDA | 2022-10-02
| Preprocesssing, and cleaning | 2022-10-19
| deciding algorithm | 2022-11-01
| optimizing algorithm | 2022-11-07
P2: Clone app | front-end | 2022-11-15
| backend | 2022-11-26
| db connectivity | 2022-11-27
| embed recommend stm & deployment | 2022-12-08